FINANCIAL DATA HUB

M3 Execution Plan

Acquisition Pipeline

Document Status: Draft for Stakeholder Review

Author: Chief Architect / Technical Program Manager

Date: 2026-06-05  |  Baseline Commit: 9770c22 (M2 Sign-Off)  |  Branch: main

# 1. Executive Summary

Milestone 3 (M3) delivers the Acquisition Pipeline -- the core data-ingestion engine that transforms the Financial Data Hub from a user-authentication and company-registry platform into an operational financial data acquisition system.

M2 established the company and job domain models, the team management workflows, and the S3 pre-signed URL scaffolding. M3 builds on top of those foundations to implement the full lifecycle from source discovery through to raw document storage in S3, ready for extraction by M4/M5.

By the end of M3, the system will be capable of:

- Resolving any company ticker or name to a canonical SEC CIK identifier

- Querying SEC EDGAR for annual (10-K) and quarterly (10-Q) filings

- Downloading source documents (XBRL, iXBRL, HTML) with integrity verification

- Storing raw artifacts to S3 with a well-defined object key convention

- Dispatching acquisition workflows as idempotent Celery jobs tracked against FinancialJob records

- Surfacing acquisition status and filing metadata through versioned REST endpoints

M3 contains 9 sub-milestones, 7 database table additions, approximately 24 new source files, and 2 new Alembic migrations. The target test coverage for new code is >= 90%, consistent with M2.

# 2. Current Architecture Assessment

## 2.1 Backend Layer

apps/api/

+-core/          config, database, email, exceptions, s3, security

+-middleware/    audit, auth (JWT/RBAC), rate_limit

+-models/        __init__.py  (all ORM models -- M1+M2 pattern)

+-repositories/  auth, companies, invitations, jobs

+-routers/       admin, auth, companies, exports, financials, invitations, jobs

+-schemas/       auth, companies, invitations, jobs

Strengths to preserve:

- UUID v7 primary keys (gen_uuid7()) -- time-ordered, B-tree safe

- All user-data tables carry tenant_id (shared schema multi-tenancy)

- Soft delete via deleted_at on entity tables; no soft delete on terminal-state records (FinancialJob)

- Async SQLAlchemy 2.x throughout; synchronous path never used in request lifecycle

- Repository layer enforces tenant isolation -- never exposed to routers

- Role-based access control: OWNER > ADMIN > ANALYST > VIEWER

Key conventions M3 must follow:

- ORM models live in apps/api/models/__init__.py

- Schemas live in apps/api/schemas/<domain>.py

- Repositories live in apps/api/repositories/<domain>.py

- Routers use prefix="/api/v1/<resource>", tags, and error codes in docstrings

- Settings are injected via get_settings() (lru_cached Settings instance)

## 2.2 Worker Layer

workers/

+-celery_app.py   Celery factory; queue routing defined

+-queues.py       QUEUE_FETCH, QUEUE_AI, QUEUE_COMPUTE, QUEUE_EXPORT, QUEUE_DEFAULT

+-tasks/acquisition_tasks.py    STUB -- "TODO M3"

Queue routing is already wired: acquisition_tasks.* -> QUEUE_FETCH.

## 2.3 Services Layer -- Acquisition Stubs

services/acquisition/

+-company_resolver/  resolver.py       STUB -- "TODO M2-Step24"

+-document_fetcher/  fetcher.py        STUB -- "TODO M3-Step30"

+-source_registry/   registry.py       STUB -- "TODO M3"

sources/sec_edgar.py  STUB -- "TODO M3"

## 2.4 Database State

Migrations applied: 001_initial_schema.py, 002_companies_jobs.py, 003_invitations.py

Gap: The source_configs table referenced in db/seeds/source_configs.sql has no migration yet. M3.1 must create it.

## 2.5 Existing Settings Relevant to M3

All required settings are already declared -- no new additions needed for M3.1-M3.6:

- edgar_user_agent, edgar_requests_per_second (10), edgar_base_url

- claude_api_key, claude_model

- s3_documents_bucket, aws_endpoint_url (LocalStack override)

# 3. M3 Objectives

| # | Objective | Success Condition |
| --- | --- | --- |
| O-1 | Source Registry operational | source_configs table migrated; SEC EDGAR config live; SourceRegistry loads and validates configurations |
| O-2 | Company resolver functional | Given any ticker or name, CompanyResolver returns a canonical Company record with cik populated |
| O-3 | Filing catalogue available | FilingRecord and FilingDocument ORM models exist; EDGAR filing lists can be persisted |
| O-4 | SEC EDGAR client wired | SECEdgarSource implements BaseSource protocol; CIK lookup, filing search, and submission JSON parsing functional |
| O-5 | Document download pipeline | DocumentFetcher streams files from EDGAR, computes SHA-256, verifies size, stores to S3 |
| O-6 | S3 storage convention | All raw documents stored at raw/{tenant_id}/{company_id}/{filing_id}/{filename} |
| O-7 | Acquisition job pipeline | run_acquisition_job Celery task orchestrates full workflow; FinancialJob status transitions correct |
| O-8 | Acquisition API endpoints | /api/v1/filings and /api/v1/acquisition endpoints deployed |
| O-9 | End-to-end validation | Complete acquisition cycle passes in Docker Compose |

# 4. M3 Architecture Overview

Data flow narrative:

- ANALYST triggers acquisition via POST /api/v1/acquisition/trigger with a job_id referencing an existing FinancialJob.

- Router transitions job to QUEUED, records celery_task_id, returns 202 Accepted immediately.

- Celery task run_acquisition_job picks up from QUEUE_FETCH; transitions job to RUNNING.

- CIK Resolution: If company.cik is NULL, CompanyResolver queries EDGAR company search to resolve and persist the CIK.

- Filing Discovery: SECEdgarSource fetches submissions JSON, extracts 10-K/10-Q metadata, persists FilingRecord rows.

- Document Fetch: DocumentFetcher streams documents, verifies SHA-256, uploads to S3 under raw/ prefix; FilingDocument rows created.

- On success: FinancialJob.status -> COMPLETED; completed_at set. On failure: status -> FAILED; error_message populated.

System architecture:

API Layer (FastAPI)

POST /api/v1/acquisition/trigger

GET  /api/v1/filings/{company_id}

GET  /api/v1/acquisition/{job_id}/status

| dispatch (job_id)

v

Celery Worker (QUEUE_FETCH)

run_acquisition_job(job_id)

|-- resolve_company_cik  -> CompanyResolver

|-- discover_filings     -> SECEdgarSource

|-- persist_filings      -> FilingRepository

+-- fetch_documents      -> DocumentFetcher -> S3 raw/

|

v

Storage

PostgreSQL: source_configs, filing_records, filing_documents

S3:         raw/{tenant_id}/{company_id}/{filing_id}/{filename}

Redis:      Rate limiter token bucket (EDGAR 10 req/sec)

# 5. Folder Structure Additions

New files to be created (all existing folders used as-is):

apps/api/repositories/filings.py           NEW -- FilingRepository

apps/api/repositories/sources.py           NEW -- SourceConfigRepository

apps/api/routers/acquisition.py            NEW -- trigger + status endpoints

apps/api/routers/filings.py                NEW -- filing list + document endpoints

apps/api/schemas/acquisition.py            NEW -- trigger request/response schemas

apps/api/schemas/filings.py                NEW -- filing and document schemas

db/migrations/versions/004_source_configs.py  NEW -- source_configs table

db/migrations/versions/005_filings.py         NEW -- filing_records, filing_documents

services/acquisition/source_registry/registry.py    IMPLEMENT

services/acquisition/source_registry/rate_limiter.py IMPLEMENT

services/acquisition/source_registry/sources/__init__.py IMPLEMENT BaseSource

services/acquisition/source_registry/sources/sec_edgar.py IMPLEMENT

services/acquisition/company_resolver/resolver.py    IMPLEMENT

services/acquisition/company_resolver/alias_manager.py IMPLEMENT

services/acquisition/document_fetcher/fetcher.py     IMPLEMENT

services/acquisition/document_fetcher/storage.py     IMPLEMENT

services/acquisition/document_fetcher/deduplicator.py IMPLEMENT

workers/tasks/acquisition_tasks.py                   IMPLEMENT

tests/unit/test_source_registry.py / test_company_resolver.py  NEW

tests/unit/test_sec_edgar_source.py / test_document_fetcher.py NEW

tests/unit/test_acquisition_tasks.py / test_acquisition_router.py / test_filings_router.py  NEW

tests/integration/test_acquisition_pipeline.py       NEW

tests/integration/test_filing_repositories.py        NEW

scripts/m3_validate.py                               NEW

# 6. Database Additions

## 6.1 Migration 004 -- source_configs

Stores configuration for each data source (SEC EDGAR, NSE, BSE, etc.) including base URLs, rate limits, and JSON config blobs. The seed file db/seeds/source_configs.sql already contains the SEC EDGAR row.

| Column | Type | Constraints | Notes |
| --- | --- | --- | --- |
| id | UUID | PK, gen_uuid7() | UUID v7 |
| name | VARCHAR(100) | NOT NULL, UNIQUE | e.g. "SEC EDGAR" |
| source_type | VARCHAR(50) | NOT NULL | regulatory ¦ exchange ¦ provider |
| country_code | VARCHAR(5) | NOT NULL | ISO 3166-1: US, IN |
| tier | INTEGER | NOT NULL, default 1 | Priority; 1=primary |
| base_url | VARCHAR(500) | NOT NULL |  |
| url_pattern | VARCHAR(1000) | NULL | Template URL with {cik} etc. |
| requires_api_key | BOOLEAN | NOT NULL, default false |  |
| rate_limit_rpm | INTEGER | NOT NULL | Requests per minute (600 for EDGAR) |
| is_active | BOOLEAN | NOT NULL, default true |  |
| config | JSONB | NULL | Source-specific config blob |
| created_at / updated_at | TIMESTAMPTZ | NOT NULL, default NOW() | Standard audit timestamps |

## 6.2 Migration 005 -- filing_records

Represents a single SEC filing (10-K, 10-Q, 8-K, etc.) discovered for a company.

| Column | Type | Constraints | Notes |
| --- | --- | --- | --- |
| id | UUID | PK, gen_uuid7() | UUID v7 |
| tenant_id | UUID | FK -> tenants.id CASCADE | Tenant isolation |
| company_id | UUID | FK -> companies.id CASCADE | Owning company |
| source_config_id | UUID | FK -> source_configs.id RESTRICT | Source used |
| job_id | UUID | FK -> financial_jobs.id SET NULL | Discovery job |
| accession_number | VARCHAR(20) | NOT NULL | SEC format: 0001234567-24-000001 |
| form_type | VARCHAR(20) | NOT NULL | 10-K, 10-Q, 8-K |
| filing_date | DATE | NOT NULL | Date filed with SEC |
| period_of_report | DATE | NULL | Period end date |
| fiscal_year / quarter | INTEGER | NULL | e.g. 2023; 1-4 or NULL for annual |
| edgar_url | VARCHAR(500) | NOT NULL | EDGAR index URL |
| xbrl_available | BOOLEAN | NOT NULL, default false | iXBRL available flag |
| is_amendment | BOOLEAN | NOT NULL, default false | 10-K/A etc. |
| fetch_status | VARCHAR(50) | NOT NULL, default pending | pending ¦ fetched ¦ failed |
| fetch_attempted_at | TIMESTAMPTZ | NULL | Last fetch attempt |
| fetch_error | TEXT | NULL | Error message on failure |
| raw_metadata | JSONB | NULL | Full submission JSON fragment |
| created_at / updated_at | TIMESTAMPTZ | NOT NULL, default NOW() |  |

Unique constraint: uq_filing_records_tenant_accession on (tenant_id, accession_number)

## 6.3 Migration 005 -- filing_documents

Represents a single file within a filing (primary document, XBRL instance, labels, etc.).

| Column | Type | Constraints | Notes |
| --- | --- | --- | --- |
| id | UUID | PK, gen_uuid7() | UUID v7 |
| filing_id | UUID | FK -> filing_records.id CASCADE | Parent filing |
| tenant_id | UUID | FK -> tenants.id CASCADE | Denormalized for isolation queries |
| document_type | VARCHAR(50) | NOT NULL | primary ¦ xbrl_instance ¦ xbrl_labels ¦ xbrl_schema ¦ htm |
| filename | VARCHAR(255) | NOT NULL | Original filename from EDGAR index |
| description | VARCHAR(500) | NULL | SEC filing index description |
| mime_type | VARCHAR(100) | NULL | application/xml, text/html, etc. |
| s3_key | VARCHAR(2000) | NULL | S3 object key under raw/ prefix |
| s3_bucket | VARCHAR(100) | NULL | Bucket name |
| sha256_hash | VARCHAR(64) | NULL | Hex SHA-256 of stored bytes |
| file_size_bytes | BIGINT | NULL | Original file size |
| download_status | VARCHAR(50) | NOT NULL, default pending | pending ¦ downloaded ¦ failed |
| download_attempted_at | TIMESTAMPTZ | NULL |  |
| download_error | TEXT | NULL |  |
| source_url | VARCHAR(2000) | NOT NULL | Full EDGAR URL |
| created_at / updated_at | TIMESTAMPTZ | NOT NULL, default NOW() |  |

Unique constraint: uq_filing_documents_filing_filename on (filing_id, filename)

# 7. ORM Models To Be Added

All models follow existing conventions in apps/api/models/__init__.py.

New Enums: FetchStatus (PENDING | FETCHED | FAILED | SKIPPED) and DownloadStatus (PENDING | DOWNLOADED | FAILED | SKIPPED).

SourceConfig: Mirrors source_configs. No tenant_id (global config). No soft delete. config field as dict[str, Any] via JSONB.

FilingRecord: Mirrors filing_records. No soft delete. @property is_pending and @property is_fetched. Relationships: company -> Company, source -> SourceConfig, documents -> list[FilingDocument].

FilingDocument: Mirrors filing_documents. Relationship: filing -> FilingRecord. @property is_stored returns True when s3_key is not None and download_status == "downloaded".

Updates to existing models:

- Tenant: Add filing_records: Mapped[list[FilingRecord]] relationship

- Company: Add filing_records: Mapped[list[FilingRecord]] relationship

- FinancialJob: Add filing_records: Mapped[list[FilingRecord]] relationship

# 8. Repository Layer Additions

## 8.1 SourceConfigRepository (read-only)

| Method | Signature | Purpose |
| --- | --- | --- |
| get_by_name | (session, name) -> SourceConfig ¦ None | Look up by name |
| get_all_active | (session) -> list[SourceConfig] | Load all is_active = True sources |
| get_by_country | (session, country_code) -> list[SourceConfig] | Country-filtered source list |

## 8.2 FilingRepository (all methods enforce tenant_id isolation)

| Method | Signature | Purpose |
| --- | --- | --- |
| create_filing | (session, tenant_id, payload) -> FilingRecord | Insert new filing; handle uq conflict silently |
| upsert_filing | (session, tenant_id, accession_number, payload) -> FilingRecord | Insert or update by accession number |
| get_by_id | (session, tenant_id, filing_id) -> FilingRecord ¦ None | Tenant-safe get |
| list_for_company | (session, tenant_id, company_id, form_type?, page, page_size) -> tuple[list, int] | Paginated filing list |
| get_pending_filings | (session, tenant_id) -> list[FilingRecord] | Filings awaiting fetch |
| mark_fetched | (session, filing_id) -> FilingRecord | Set fetch_status = FETCHED |
| mark_fetch_failed | (session, filing_id, error) -> FilingRecord | Set fetch_status = FAILED, store error |
| create_document | (session, payload) -> FilingDocument | Insert document row |
| upsert_document | (session, filing_id, filename, payload) -> FilingDocument | Insert or update by (filing_id, filename) |
| mark_document_downloaded | (session, doc_id, s3_key, sha256, size) -> FilingDocument | Finalize download, set S3 key and hash |
| mark_document_failed | (session, doc_id, error) -> FilingDocument | Record failure |
| list_pending_documents | (session, filing_id) -> list[FilingDocument] | Documents awaiting download |

# 9. Service Layer Additions

## 9.1 SourceRegistry

Purpose: Runtime registry of available data sources. Loaded from the database on startup, cached in-process with a 5-minute TTL.

- SourceRegistry.get_source(name) -> BaseSource

- SourceRegistry.list_sources(country_code?) -> list[SourceConfig]

- SourceRegistry.health_check() -> dict[str, bool]

## 9.2 BaseSource Protocol

Defines the contract all data sources must satisfy. All return types are dataclasses (not ORM models):

- search_company(query: str) -> list[CompanySearchResult]

- get_filings(cik: str, form_types: list[str], max_filings: int) -> list[FilingMetadata]

- get_filing_documents(accession_number: str) -> list[DocumentMetadata]

- build_document_url(cik: str, accession_number: str, filename: str) -> str

## 9.3 SECEdgarSource

Concrete implementation of BaseSource for the SEC EDGAR API.

- Uses httpx.AsyncClient for all HTTP calls

- Sets User-Agent header from settings.edgar_user_agent on every request (SEC fair access policy)

- Calls data.sec.gov/submissions/CIK{cik_padded}.json for filing metadata

- Uses RateLimiter (token bucket) to enforce settings.edgar_requests_per_second (10/s)

- On HTTP 429, performs exponential backoff with jitter (max 3 retries)

- Builds document URLs: https://www.sec.gov/Archives/edgar/data/{cik}/{accession_clean}/{filename}

CIK resolution flow (3 fallback strategies):

- Query data.sec.gov/submissions/CIK{cik_padded}.json if CIK already known

- If not, query efts.sec.gov/LATEST/search-index?q="{ticker}"&forms=10-K

- Fall back to company name search if ticker search yields no results

- Raise CompanyNotResolvedError if all three strategies fail

## 9.4 RateLimiter

Redis-backed token bucket rate limiter using Redis.eval() with a Lua script for atomic check-and-consume across multiple Celery workers. Key: fdh:rate_limit:{source_name}.

## 9.5 CompanyResolver

Resolves a Company ORM record (cik = NULL) to a fully identified company. Persists resolved CIK back to the database. Raises CIKResolutionError (triggers job -> FAILED) if unresolvable after all strategies.

## 9.6-9.9 DocumentFetcher / Deduplicator / AliasManager / DocumentStorage

DocumentFetcher: Streams downloads via httpx (stream=True). Computes SHA-256 incrementally. Checks Deduplicator before uploading. Sets x-amz-meta-sha256, x-amz-meta-filing-id, x-amz-meta-source on S3 object. Verifies Content-Length integrity.

Deduplicator: Detects duplicate downloads by checking sha256_hash in filing_documents. Returns existing FilingDocument to enable s3_key reuse without re-upload.

AliasManager: Manages company name aliases (e.g., "Meta" <-> "Facebook"). DB-backed using field_aliases seed data.

DocumentStorage: Enforces S3 key convention raw/{tenant_id}/{company_id}/{filing_id}/{filename}. Wraps apps/api/core/s3.py client.

# 10. API Endpoint Additions

## 10.1 Router: /api/v1/acquisition

| Method | Path | Auth | Purpose |
| --- | --- | --- | --- |
| POST | /trigger | require_analyst | Dispatch acquisition for an existing FinancialJob; job -> QUEUED; returns 202 Accepted |
| GET | /{job_id}/status | require_authenticated | Return current FinancialJob status with fetch_status counts for filing records |
| POST | /{job_id}/retry | require_analyst | Re-queue a FAILED job; resets status to PENDING; idempotent |

AcquisitionTriggerRequest body: job_id (UUID), form_types (list[str], default ["10-K"]), max_filings (int, default 5, max 20), fiscal_years (list[int] | None).

## 10.2 Router: /api/v1/filings

| Method | Path | Auth | Purpose |
| --- | --- | --- | --- |
| GET | /{company_id} | require_authenticated | List FilingRecord rows; paginated; filterable by form_type, fiscal_year |
| GET | /{company_id}/{filing_id} | require_authenticated | Single FilingRecord with nested FilingDocument list |
| GET | /{company_id}/{filing_id}/documents | require_authenticated | List all FilingDocument rows for a filing |
| GET | /{company_id}/{filing_id}/documents/{doc_id}/download | require_authenticated | Generate pre-signed S3 URL for raw document (expiry: 86400s) |

## 10.3 Updates to Existing Routers

GET /api/v1/companies/{id}: Add filing_count field to CompanyResponse schema.

GET /api/v1/jobs/{id}: Add acquisition_summary (filing_records_total, filing_records_fetched, filing_records_failed, documents_total, documents_downloaded, documents_failed) to FinancialJobResponse.

# 11. Queue / Background Job Architecture

## 11.1 Task: run_acquisition_job

Queue: QUEUE_FETCH  |  Module: workers.tasks.acquisition_tasks

| Configuration Setting | Value |
| --- | --- |
| max_retries | 3 |
| default_retry_delay | 60 seconds |
| acks_late | True |
| reject_on_worker_lost | True |
| soft_time_limit | 600 seconds |
| time_limit | 720 seconds |

Step sequence:

- Load FinancialJob by job_id; verify status == QUEUED

- Transition job -> RUNNING; set started_at = now()

- Load Company for job.company_id

- [CIK Resolution] CompanyResolver.resolve(company) -- updates cik if NULL; raises CIKResolutionError on failure

- [Filing Discovery] SECEdgarSource.get_filings(cik, form_types, max_filings) -- returns list[FilingMetadata]

- [Persist Filings] For each FilingMetadata: FilingRepository.upsert_filing(session, tenant_id, metadata)

- [Document Discovery] For each FilingRecord: get_filing_documents(); upsert_document() for each

- [Document Download] For each pending FilingDocument: DocumentFetcher.fetch(); mark downloaded or failed; continue

- [Evaluate] All downloaded -> COMPLETED; some failed -> COMPLETED with warnings in error_message; critical failure -> FAILED

Idempotency: Task checks FinancialJob.status at Step 1. If not QUEUED, returns immediately. upsert_filing and upsert_document use unique constraints to handle duplicate executions safely.

## 11.2 Task Chaining Strategy

M3 uses a single monolithic task (run_acquisition_job). The entire pipeline is I/O-bound, runs on QUEUE_FETCH, and completes within the 720-second limit. A single task provides simpler retry semantics and a cleaner status model.

M4+ consideration: When extraction is added (Claude API on QUEUE_AI), the pipeline will split into run_acquisition_job -> run_extraction_job using Celery chord or chain.

# 12. S3 Storage Strategy

Bucket: settings.s3_documents_bucket (fdh-documents-dev). No new bucket is created.

## 12.1 Object Key Convention

Pattern: raw/{tenant_id}/{company_id}/{filing_id}/{filename}

- raw/ prefix -- clearly separates raw source artifacts from processed outputs (exports/ prefix used by M2)

- {filing_id} segment -- UUID v7, maps directly to filing_records.id; no guesswork

- {filename} -- original filename from the EDGAR filing index, preserving SEC naming conventions

- No date segment in the key -- filing_date is in the FilingRecord and on the S3 object metadata

## 12.2 S3 Object Metadata Headers

Every uploaded object includes:

- x-amz-meta-tenant-id, x-amz-meta-company-id, x-amz-meta-filing-id

- x-amz-meta-accession-number, x-amz-meta-form-type

- x-amz-meta-sha256, x-amz-meta-source: sec_edgar

- x-amz-meta-document-type: primary | xbrl_instance | ...

## 12.3 Pre-Signed URL Generation

GET /api/v1/filings/{company_id}/{filing_id}/documents/{doc_id}/download generates a pre-signed GET URL via apps/api/core/s3.py. Expiry: settings.export_signed_url_expiry_seconds (86400 seconds = 24 hours).

# 13. Security Considerations

| Area | Requirement | Implementation |
| --- | --- | --- |
| SEC EDGAR Fair Access | User-Agent header on all EDGAR requests | settings.edgar_user_agent injected on every httpx call; integration test asserts header presence |
| Rate Limiting | Max 10 req/sec to EDGAR | Redis-backed token bucket via Lua script; atomic across all Celery workers; key: fdh:rate_limit:sec_edgar |
| S3 Key Isolation | No cross-tenant S3 key collisions | tenant_id as first path segment in all raw/ keys; FilingRepository enforces tenant isolation on all queries |
| SHA-256 Integrity | Detect corrupted downloads | SHA-256 computed incrementally during streaming; stored in FilingDocument.sha256_hash and S3 metadata |
| URL Injection Prevention | Prevent EDGAR URL manipulation | CIK validated r"^\d{1,10}$"; accession number r"^\d{10}-\d{2}-\d{6}$"; user input never interpolated into HTTP URLs |
| Sensitive Data in Logs | Prevent credential/URL leakage | Pre-signed URL query params dropped by structlog processor; EDGAR responses not logged at DEBUG in production |
| SSRF Prevention | Restrict outbound to SEC domains | Domain allowlist check before any fetch: parsed_url.netloc must match r"^[\w.-]+\.sec\.gov$" |

# 14. Error Handling Strategy

## 14.1 Error Taxonomy

| Error Class | Where Raised | Handling |
| --- | --- | --- |
| CIKResolutionError | CompanyResolver | Task -> FAILED; error_message set; no retry |
| FilingDiscoveryError | SECEdgarSource.get_filings | Task retried up to 3x; then -> FAILED |
| DocumentDownloadError | DocumentFetcher | Document marked FAILED; task continues |
| IntegrityError (checksum) | DocumentFetcher | Document marked FAILED and re-queued once |
| RateLimitTimeoutError | RateLimiter | Task retried after backoff |
| httpx.TimeoutException | Any EDGAR call | Retry with exponential backoff (3 attempts) |
| httpx.HTTPStatusError 404 | Document fetch | Document marked FAILED; non-fatal; pipeline continues |
| httpx.HTTPStatusError 429 | Any EDGAR call | Respect Retry-After header; back off |
| httpx.HTTPStatusError 5xx | Any EDGAR call | Retry; classify as transient |
| S3UploadError | DocumentStorage | Document marked FAILED; task may retry |
| DatabaseConnectionError | Any DB operation | Task retried; broker requeues if worker lost |

## 14.2 Job-Level Failure Semantics

FAILED: CIK cannot be resolved after all strategies exhausted; EDGAR returns 5xx on all retries for filing discovery; database unavailable.

COMPLETED (with warnings): Filing records created but some documents failed; summary written to FinancialJob.error_message.

COMPLETED (clean): All documents downloaded and SHA-256 verified; error_message = None.

## 14.3 Observability

Structured log events emitted via structlog:

- acquisition.cik_resolved -- {company_id, cik, source}

- acquisition.filing_discovered -- {company_id, accession_number, form_type}

- acquisition.document_fetched -- {filing_id, doc_id, s3_key, sha256, bytes}

- acquisition.document_failed -- {filing_id, doc_id, url, error}

- acquisition.job_completed -- {job_id, filings_total, docs_total, docs_failed}

# 15. Testing Strategy

## 15.1 Unit Tests

| Test File | Coverage Target |
| --- | --- |
| test_source_registry.py | Registry load, source instantiation, health check |
| test_company_resolver.py | CIK resolution happy path, all fallback strategies, CIKResolutionError |
| test_sec_edgar_source.py | search_company, get_filings, get_filing_documents, User-Agent assertion, rate limit retry, 429 handling |
| test_document_fetcher.py | Stream download, SHA-256 compute, deduplication, integrity failure, S3 upload |
| test_acquisition_tasks.py | Task happy path, partial failure (some docs fail), CIK failure -> FAILED, idempotency on re-run |
| test_acquisition_router.py | POST /trigger validation, 202 response, job state transition, retry endpoint |
| test_filings_router.py | List filings, get single filing, pre-signed URL generation |

## 15.2 Integration Tests

| Test File | Coverage Target |
| --- | --- |
| test_acquisition_pipeline.py | Full pipeline: create company -> trigger job -> worker runs -> documents in S3 -> job COMPLETED |
| test_filing_repositories.py | FilingRepository CRUD, upsert idempotency, tenant isolation |

## 15.3 EDGAR Fixtures

Stored in tests/fixtures/edgar/: aapl_submissions.json, aapl_10k_index.json, aapl_10k_primary.htm (10KB sample), msft_submissions.json. These fixtures are recorded from real EDGAR responses, sanitized, and committed to the repository. Tests never make live EDGAR calls.

## 15.4 Coverage Requirements

- Overall target: >= 90% (consistent with M2 requirement)

- Acquisition service layer: >= 95% (critical pipeline code)

- Worker tasks: >= 90% (all branches including failure modes)

- Routers: >= 90%

# 16. Validation Gates

| Gate | Check | Pass Criterion |
| --- | --- | --- |
| VG-01 | Alembic clean | alembic check exits 0; no pending migrations |
| VG-02 | Migration 004 | source_configs table exists; SEC EDGAR seed row present with rate_limit_rpm = 600 |
| VG-03 | Migration 005 | filing_records and filing_documents tables exist with all columns |
| VG-04 | ORM models | FilingRecord, FilingDocument, SourceConfig importable from apps.api.models |
| VG-05 | Source registry | SourceRegistry().get_source("SEC EDGAR") returns SECEdgarSource instance |
| VG-06 | CIK resolution | Given ticker "AAPL", CompanyResolver.resolve() returns CIK = "0000320193" (mocked) |
| VG-07 | SEC EDGAR source | SECEdgarSource.get_filings("0000320193", ["10-K"], 5) returns >= 1 FilingMetadata from fixture |
| VG-08 | Document fetcher | DocumentFetcher.fetch() uploads test fixture to LocalStack S3; SHA-256 verified |
| VG-09 | Task execution | run_acquisition_job.delay(job_id) completes; FinancialJob.status == "completed" |
| VG-10 | Idempotency | Running run_acquisition_job.delay(job_id) twice produces identical DB state |
| VG-11 | API trigger | POST /api/v1/acquisition/trigger returns 202; job transitions to QUEUED |
| VG-12 | Filing list | GET /api/v1/filings/{company_id} returns paginated list of filing records |
| VG-13 | Pre-signed URL | GET .../documents/{doc_id}/download returns a valid pre-signed S3 URL |
| VG-14 | Test suite | pytest passes; >= 90% coverage; 0 failures; 0 errors |

# 17. Acceptance Criteria

M3 is signed off when all of the following are demonstrably true:

- Database: Migrations 004 and 005 apply cleanly; alembic downgrade -1 then alembic upgrade head executes without error.

- Seed data: source_configs table contains the SEC EDGAR row with rate_limit_rpm = 600, tier = 1, is_active = true.

- CIK resolution: Company with ticker = "AAPL" and cik = NULL results in cik = "0000320193" persisted to the database.

- Filing discovery: Pipeline discovers and persists >= 1 FilingRecord with form_type = "10-K", non-null accession_number, non-null period_of_report.

- Document storage: Primary document of most recent 10-K in LocalStack S3 at raw/{tenant_id}/{company_id}/{filing_id}/{filename}.

- SHA-256 integrity: Every FilingDocument with download_status = "downloaded" has non-null sha256_hash matching the S3 object.

- Job lifecycle: FinancialJob transitions through PENDING -> QUEUED -> RUNNING -> COMPLETED with all timestamps correct.

- API contract: All new endpoints return documented HTTP status codes; 422 errors conform to existing error schema in apps/api/core/exceptions.py.

- Test suite: pytest reports >= 90% coverage; M2 tests continue to pass (0 regressions).

- Docker Compose: Full pipeline completes within 120 seconds for a 5-filing acquisition.

# 18. Milestone Breakdown

## M3.1 -- Source Registry

Purpose: Create the source_configs table and implement SourceRegistry that loads, validates, and vends data source configurations at runtime.

Deliverables: Migration 004; SourceConfig ORM model; SourceConfigRepository; SourceRegistry with in-process caching; BaseSource protocol; SEC EDGAR seed data applied; unit tests.

Dependencies: M2 complete  |  Validation Gates: VG-01, VG-02, VG-05  |  Estimated Complexity: Low (1-2 days)

Risk R-01 (Low): Ensure migration runs before seeding in Docker Compose init sequence.

Definition of Done: Migration 004 applies cleanly. SourceRegistry().get_source("SEC EDGAR") returns non-null instance cached after first call. Unit tests >= 95% coverage of registry.py.

## M3.2 -- Company Resolver

Purpose: Implement CompanyResolver that resolves a Company record's cik field using SEC EDGAR company search API with all three fallback strategies.

Deliverables: CompanyResolver (resolver.py); AliasManager (alias_manager.py with DB-backed alias lookup); EDGAR fixture aapl_company_search.json; unit tests.

Dependencies: M3.1  |  Validation Gates: VG-06  |  Estimated Complexity: Medium (2-3 days)

Risk R-02 (Medium): EDGAR search returns multiple matches for common names -- implement confidence-ranking: exact ticker > exact name > fuzzy match.

Risk R-03 (Low): Confirm alias table uses company names, not financial field names.

Definition of Done: CompanyResolver.resolve() sets cik for AAPL to 0000320193 using fixture. CIKResolutionError raised when all strategies fail.

## M3.3 -- Filing Models

Purpose: Create filing_records and filing_documents database tables and their ORM models. Delivers the persistence layer without requiring EDGAR integration.

Deliverables: Migration 005; FetchStatus and DownloadStatus enums; FilingRecord and FilingDocument ORM models with all columns, indexes, and relationships; FilingRepository with all CRUD methods; relationship updates to Company, Tenant, FinancialJob.

Dependencies: M3.1  |  Validation Gates: VG-03, VG-04, VG-01  |  Estimated Complexity: Medium (2 days)

Risk R-04 (Low): Enforce accession number canonical form with dashes (0001234567-24-000001) in FilingRepository.upsert_filing().

Definition of Done: Migration 005 applies and rolls back cleanly. upsert_filing() called twice with same accession number returns same record without error.

## M3.4 -- SEC EDGAR Integration

Purpose: Implement SECEdgarSource -- the concrete EDGAR API client. Most technically complex single component in M3.

Deliverables: SECEdgarSource (complete BaseSource implementation); RateLimiter (Redis token bucket with Lua script); EDGAR fixtures (aapl_submissions.json, aapl_10k_index.json); comprehensive unit tests covering all code paths.

Dependencies: M3.1, M3.2  |  Validation Gates: VG-05, VG-06, VG-07  |  Estimated Complexity: High (3-4 days)

Risk R-05 (High): EDGAR submissions JSON schema is unversioned -- use .get() throughout; test with AAPL, MSFT, and small-cap fixtures to cover schema variations.

Risk R-06 (Medium): filings.recent limited to ~1000 filings -- confirm if paginated older block needed for MVP.

Risk R-07 (Low): Lua rate limiter script must be idempotent on Redis restart; use SETNX pattern.

Definition of Done: get_filings returns >= 1 FilingMetadata from AAPL fixture. User-Agent assertion passes. Rate limiter holds to 10/sec. 429 triggers Retry-After-aware backoff.

## M3.5 -- Document Fetcher

Purpose: Implement DocumentFetcher, Deduplicator, and DocumentStorage -- the download-verify-store pipeline for raw filing documents.

Deliverables: DocumentFetcher (streaming download with SHA-256); Deduplicator (hash-based duplicate detection); DocumentStorage (S3 upload with key convention and metadata); unit tests.

Dependencies: M3.3, M3.4  |  Validation Gates: VG-08  |  Estimated Complexity: Medium-High (2-3 days)

Risk R-08 (Medium): EDGAR iXBRL documents can be 50-200 MB -- must stream with backpressure; never accumulate full file in memory.

Risk R-09 (Low): Content-Length may be absent on some EDGAR responses -- tolerate missing header; still verify SHA-256.

Definition of Done: fetch() uploads 10MB fixture to LocalStack without full memory buffering. SHA-256 mismatch raises IntegrityError. Duplicate SHA-256 returns existing record without re-uploading.

## M3.6 -- S3 Storage Pipeline

Purpose: Validate end-to-end that documents are stored under the correct S3 key convention and are retrievable via pre-signed URLs.

Deliverables: DocumentStorage.build_key() with unit test; S3 metadata headers verified in integration test; pre-signed URL generation for FilingDocument; download endpoint implemented.

Dependencies: M3.5, M3.3  |  Validation Gates: VG-08 (extended), VG-13  |  Estimated Complexity: Low-Medium (1-2 days)

Risk R-10 (Low): LocalStack pre-signed URL format may differ from real AWS -- use settings.aws_endpoint_url when building S3 clients in tests.

Definition of Done: Object stored at raw/{tenant_id}/{company_id}/{filing_id}/{filename}. x-amz-meta-sha256 present. Pre-signed URL endpoint returns 200 with usable URL.

## M3.7 -- Acquisition Jobs

Purpose: Implement the run_acquisition_job Celery task orchestrating the complete pipeline, managing FinancialJob status transitions, and handling all error cases.

Deliverables: run_acquisition_job task (full implementation); AcquisitionTriggerRequest / AcquisitionTriggerResponse Pydantic schemas; status transition logic; idempotency verification; unit tests.

Dependencies: M3.2, M3.3, M3.4, M3.5  |  Validation Gates: VG-09, VG-10  |  Estimated Complexity: High (3-4 days)

Risk R-11 (Medium): Idempotency must handle partial state on worker restart -- use two-phase approach: upload to S3 first, then update DB; check download_status == "downloaded" before re-uploading.

Risk R-12 (Low): Add settings.acquisition_soft_time_limit_seconds override (default 600) for tuning without code changes.

Definition of Done: Task transitions through all states correctly. Running task twice with same job_id produces identical DB state. Simulated worker restart resumes correctly.

## M3.8 -- Acquisition APIs

Purpose: Implement all new REST endpoints: acquisition trigger, job status, filing list, and document download endpoints. Wire into FastAPI application.

Deliverables: apps/api/routers/acquisition.py and filings.py; schemas/acquisition.py and filings.py; router registration in main.py; CompanyResponse and FinancialJobResponse schema updates; unit tests for both routers.

Dependencies: M3.7, M3.3, M3.6  |  Validation Gates: VG-11, VG-12, VG-13  |  Estimated Complexity: Medium (2-3 days)

Risk R-13 (Low): POST /trigger must validate FinancialJob belongs to caller's tenant -- reuse require_analyst + JobRepository.get_by_id(tenant_id, job_id).

Definition of Done: All 7 endpoints return correct HTTP status codes. OpenAPI schema includes all new endpoints with correct request/response schemas.

## M3.9 -- End-to-End Validation

Purpose: Validate the complete acquisition pipeline in Docker Compose. Execute the M3 validation gate script and produce sign-off evidence.

Deliverables: scripts/m3_validate.py (automated gate script); test_acquisition_pipeline.py; full test suite passing with >= 90% coverage; M3 Closure Report (separate document).

Dependencies: M3.1-M3.8 all complete  |  Validation Gates: VG-01 through VG-14  |  Estimated Complexity: Low-Medium (1-2 days)

Risk R-14 (Medium): LocalStack multipart upload for files > 5 MB may differ -- test with 15 MB fixture; implement multipart upload in DocumentStorage.

Risk R-15 (Low): CI/CD pipeline (.github/workflows/pr.yml) must be updated to start Celery worker container during integration tests.

Definition of Done: All 14 validation gates pass. pytest >= 90% coverage, 0 failures, 0 errors. m3_validate.py exits 0. Docker Compose pipeline completes end-to-end.

# 19. M3 Master Execution Roadmap

## 19.1 Implementation Order

The milestones must be executed in dependency order. M3.4 and M3.5 can begin concurrently after M3.3 is complete.

M3.1 Source Registry

+-> M3.2 Company Resolver

+-> M3.3 Filing Models

|-> M3.4 SEC EDGAR Integration --+

+-> M3.5 Document Fetcher --------+

+-> M3.6 S3 Storage Pipeline

|

+-> M3.7 Acquisition Jobs

|

M3.8 Acquisition APIs

|

M3.9 End-to-End Validation

## 19.2 Milestone Execution Table

| Priority | Milestone | Estimated Effort | Prerequisites | Expected Output |
| --- | --- | --- | --- | --- |
| P0 | M3.1 Source Registry | 1-2 days | M2 complete | Migration 004; SourceRegistry operational; VG-01, VG-02, VG-05 pass |
| P0 | M3.2 Company Resolver | 2-3 days | M3.1 | CIK resolution for AAPL verified; VG-06 passes |
| P0 | M3.3 Filing Models | 2 days | M3.1 | Migration 005; FilingRepository tested; VG-03, VG-04 pass |
| P1 | M3.4 SEC EDGAR Integration | 3-4 days | M3.1, M3.2 | SECEdgarSource complete; rate limiter operational; VG-07 passes |
| P1 | M3.5 Document Fetcher | 2-3 days | M3.3 | Streaming download to LocalStack; SHA-256 confirmed; VG-08 passes |
| P2 | M3.6 S3 Storage Pipeline | 1-2 days | M3.5, M3.3 | S3 key convention validated; pre-signed URL deployed; VG-13 passes |
| P2 | M3.7 Acquisition Jobs | 3-4 days | M3.2, M3.3, M3.4, M3.5 | run_acquisition_job complete; idempotency verified; VG-09, VG-10 pass |
| P3 | M3.8 Acquisition APIs | 2-3 days | M3.7, M3.3, M3.6 | All 7 endpoints deployed; OpenAPI updated; VG-11, VG-12 pass |
| P4 | M3.9 End-to-End Validation | 1-2 days | M3.1-M3.8 complete | All 14 VGs pass; pytest >= 90%; Docker Compose verified; M3 signed off |

Total estimated effort: 17-25 engineering days (3.5-5 weeks for a single engineer).

## 19.3 Parallel Work Opportunities

M3.4 and M3.5 in parallel: Once M3.3 is complete, SEC EDGAR Integration (M3.4) and Document Fetcher (M3.5) have no dependency on each other and can be developed simultaneously, reducing the critical path by 2-3 days.

M3.8 scaffolding during M3.7: The router shell (schemas, empty handlers returning 501 Not Implemented) can be scaffolded during M3.7 so the OpenAPI contract is visible in development before the task is complete.

## 19.4 Go / No-Go Criteria for M3 Sign-Off

M3 is ready for sign-off (and M4 kickoff) when:

- All 14 validation gates pass (automated by scripts/m3_validate.py)

- pytest exits 0; >= 90% overall coverage; >= 95% acquisition service coverage

- alembic check exits 0 (clean migration state)

- Docker Compose docker compose up --wait starts all services healthy

- No "TODO M3" comments remain in any production source file

- M3 Closure Report reviewed and signed by project lead

- Git tag m3-complete applied to the merge commit on main