PHASE 1 IMPLEMENTATION GUIDE

Financial Data Hub — Step-by-Step Execution Plan

| Purpose | Hand-off guide for implementation session |
| --- | --- |
| Scope | Phase 1: US Public Companies, Annual Financials, Excel Export |
| Status | Approved for implementation — all blockers resolved |
| Date | June 2, 2026 |
| Prerequisite | Engineering Specification Parts 1–3 (complete) |
| Readiness Score | 84/100 — Ready for implementation |

# 1. Repository Creation Plan

Execute in this exact order before writing any application code.

Step 1 — Create GitHub Repository

• Repository name: financial-data-hub

• Visibility: Private

• Initialise with README.md only — no template, no .gitignore yet (added manually)

• Default branch: main

• Branch protection on main: require PR review, require CI passing, no direct push

Step 2 — Clone and Initialise Local Structure

• git clone git@github.com:your-org/financial-data-hub.git

• Create root-level files: .gitignore, pyproject.toml, README.md, .env.example

• .gitignore must exclude: .env, __pycache__, .venv, *.pyc, .DS_Store, node_modules, .next

• Create the full folder structure (see Section 4) before writing any Python or TypeScript

Step 3 — Python Project Initialisation

• Tool: uv (recommended) or Poetry

• uv init — creates pyproject.toml with Python 3.12+ constraint

• uv venv — creates .venv

• Add all Python dependencies to pyproject.toml (see Section 6)

• uv sync — installs all dependencies into .venv

Step 4 — Node.js Project Initialisation (Frontend)

• cd apps/web

• npx create-next-app@latest . --typescript --tailwind --app --src-dir --no-git

• Install additional frontend packages (see Section 6)

• Configure tsconfig.json: strict mode, path aliases (@/* -> ./src/*)

• Configure tailwind.config.ts with custom colour tokens

Step 5 — Git Configuration

• Create .github/workflows/ directory with three workflow files: pr.yml, staging.yml, release.yml

• Add .github/PULL_REQUEST_TEMPLATE.md

• First commit: "chore: initialise repository structure"

• Push to main — verify branch protection rules activate

• Create develop branch from main for ongoing work

# 2. Phase 1 Build Plan

14 weeks. 8 milestones. Each milestone has a hard gate — do not proceed until the gate passes.

| ID | Milestone | Timeline | Duration | Deliverables | Success Gate |
| --- | --- | --- | --- | --- | --- |
| M0 | Pre-Development | Week 0 | 1 week | Blockers resolved, repo created, local stack running, first Alembic migration executed | All Docker services healthy. GET /health/ready returns 200. |
| M1 | Foundation Layer | Weeks 1–2 | 2 weeks | FastAPI skeleton, JWT auth, database session, audit middleware, standard error schema | Register + login + refresh + logout endpoints work end-to-end with real PostgreSQL. |
| M2 | Company Resolution | Week 3 | 1 week | SEC EDGAR company search, fuzzy matching, job creation, job status API, SSE skeleton | POST /api/v1/jobs with "Apple" resolves to Apple Inc. (AAPL) in the companies table. |
| M3 | Document Acquisition | Weeks 4–5 | 2 weeks | EDGAR 10-K discovery, SHA-256 deduplication, S3 upload, documents table, job_steps logging, EDGAR rate limiter | 5 Apple 10-K files stored in S3. documents table has 5 records. No EDGAR rate limit hit. |
| M4 | XBRL Extraction | Weeks 6–7 | 2 weeks | iXBRL parser, XBRL concept → canonical field mapping, all 3 statements, unit + currency normalisation, ratios | Apple FY2024 revenue matches published $391.04B within 0.1%. Balance sheet extracted. |
| M5 | Validation Engine | Week 8 | 1 week | 13 validation rules (IS-001 through CF-003, TR-001 through TR-004), confidence score, export blocking | Apple balance sheet passes BS-001 (assets = liabilities + equity within 0.1%). |
| M6 | Excel Export | Weeks 9–10 | 2 weeks | pandas pivot transformer, openpyxl 10-sheet workbook, S3 export upload, signed URL endpoint | Download Apple XLSX. Open in Excel. FY2024 revenue = $391.04B. Balance sheet balances. No errors. |
| M7 | Frontend MVP | Week 11 | 1 week | Login/register, dashboard, company search, SSE progress tracker, export download | Non-technical user completes full flow (search → generate → download) without instructions. |
| M8 | Hardening + Launch | Weeks 12–14 | 3 weeks | Extraction benchmarks (5 companies), email service, Celery Beat, monitoring, production deploy | Extraction accuracy >= 98%. Production smoke test passes. CI pipeline green. |

# 3. Exact Implementation Order

Each item must be complete before moving to the next. Dependencies run top to bottom.

WEEK 0 — PRE-DEVELOPMENT

1.  Resolve and document all environment variables in .env.example

2.  Set up AWS account — create S3 buckets (fdh-documents-dev, fdh-exports-dev, fdh-assets-dev)

3.  Create Secrets Manager entries: DB_PASSWORD, REDIS_URL, CLAUDE_API_KEY, JWT_SECRET

4.  Write docker-compose.yml with all 10 services (db, redis, localstack, api, 4 workers, flower, web)

5.  Verify docker compose up --build brings all services healthy

6.  Write and run Alembic migration 001 — create all tables from Engineering Spec schema

7.  Write seed SQL files: canonical_fields.sql, field_aliases.sql, source_configs.sql

8.  Run seeds. Verify 22 canonical income statement fields, 17 balance sheet, 15 cash flow exist

9.  Manual proof-of-concept: download Apple 10-K iXBRL from EDGAR, parse 3 tags with arelle/python-xbrl

WEEKS 1–2 — FOUNDATION

10. FastAPI main.py — app factory, CORS, lifespan events, /health, /health/ready

11. Pydantic Settings — all env vars typed, loaded from environment

12. SQLAlchemy async session factory — engine, session maker, get_db dependency

13. Standard error response schema — APIError Pydantic model, exception handlers

14. Auth middleware — JWT decode, attach tenant_id + user_id to request.state

15. Audit middleware — write every request to audit_log (async, non-blocking)

16. Rate limiter middleware — Redis sliding window, returns 429 with headers

17. POST /auth/register — create tenant + user, return access token + set refresh cookie

18. POST /auth/login — validate bcrypt hash, return tokens

19. POST /auth/refresh — rotate refresh token, return new access token

20. POST /auth/logout — add token to Redis blocklist, clear cookie

21. POST /auth/forgot-password — generate reset token, queue email Celery task

22. POST /auth/reset-password — validate token, update password hash

23. Email service — ConsoleEmailBackend for local dev, Jinja2 templates for 5 email types

WEEK 3 — COMPANY RESOLUTION

24. SEC EDGAR company search API wrapper — search by name and ticker

25. Company resolver — EDGAR result → companies + company_aliases records

26. Fuzzy match via pg_trgm — handle typos, abbreviations, alias lookups

27. POST /api/v1/jobs — create job record, dispatch resolve_company Celery task, return 202

28. GET /api/v1/jobs/{id} — return job with step breakdown

29. GET /api/v1/jobs/{id}/stream — SSE endpoint skeleton (broadcasts job_steps events)

WEEKS 4–5 — DOCUMENT ACQUISITION

30. SEC EDGAR filing index API — discover 10-K filings for company + last 5 fiscal years

31. Document fetcher — download filing with streaming, compute SHA-256, check for duplicates

32. S3 storage backend — upload to fdh-documents-dev with standard key convention

33. LocalStack S3 — verify uploads work locally without AWS credentials

34. documents table — populate on each fetch (metadata, content_hash, storage_path)

35. job_steps table — write step records at start and end of each fetch task

36. EDGAR rate limiter — Redis token bucket, 10 req/sec, correct User-Agent header

37. Deduplication — if content_hash exists in documents, skip download, reuse record

WEEKS 6–7 — XBRL EXTRACTION

38. iXBRL parser — use arelle or python-xbrl to parse EDGAR iXBRL HTML filing

39. XBRL concept mapper — map us-gaap: concepts to canonical_field via field_aliases table

40. Context resolver — extract period (instant vs duration), entity, unit, decimal precision

41. Income Statement extraction — all 20 canonical fields from iXBRL

42. Balance Sheet extraction — all 17 canonical fields from iXBRL

43. Cash Flow extraction — all 15 canonical fields from iXBRL

44. Unit normaliser — detect millions/thousands/billions, multiply to absolute value

45. financial_statements + financial_line_items — populate with extracted values + provenance

46. Ratio calculator — compute 16 ratios from line items, write to ratios table

WEEK 8 — VALIDATION ENGINE

47. Rule IS-001: gross_profit = revenue - cost_of_revenue (±0.5%)

48. Rule IS-002: operating_income = gross_profit - total_operating_expenses (±0.5%)

49. Rule IS-004: ebitda = operating_income + depreciation_amortization (±1.0%)

50. Rule IS-005: diluted_eps = net_income_parent / diluted_shares (±1.0%)

51. Rule BS-001: total_assets = total_liabilities + total_equity (±0.1%) — CRITICAL

52. Rules BS-002, BS-003: current subtotals <= totals

53. Rule CF-001: operations + investing + financing + fx = net_change_in_cash (±0.5%)

54. Rule CF-002: free_cash_flow = operations + capex (±0.1%)

55. Rules TR-001 through TR-004: trend anomaly detection

56. Confidence score calculator — 100 base, apply deductions per rule severity

57. Export blocking policy — < 40 score or unresolved CRITICAL blocks export generation

58. validation_results table — write every rule execution (pass or fail)

WEEKS 9–10 — EXCEL EXPORT

59. pandas transformer — query financial_line_items, pivot to (canonical_field × fiscal_year) DataFrame

60. YoY growth DataFrame — pct_change across year columns

61. Confidence overlay DataFrame — parallel structure for conditional cell formatting

62. openpyxl workbook builder — Sheet 1 (Company Overview) with all metadata

63. Sheet 2 — Income Statement: formatted rows, YoY growth columns, section headers

64. Sheet 3 — Balance Sheet: same structure

65. Sheet 4 — Cash Flow: same structure

66. Sheet 5 — Ratios: computed from ratios table, formulas referencing Sheets 2–4

67. Sheets 6–7 — Segments and Strategic Initiatives (placeholder rows, Phase 4–5 note)

68. Sheet 8 — Data Sources: document table with URLs, tiers, extraction methods

69. Sheet 9 — Validation Report: all validation_results colour-coded by severity

70. Sheet 10 — Metadata: job ID, timestamp, template version v1.0.0, model version

71. Apply global formatting: freeze panes, column widths, number formats, yellow highlight for confidence < 80%

72. Upload workbook to fdh-exports-dev S3 bucket, write exports table record

73. GET /api/v1/exports/{id}/download-url — generate 24-hour pre-signed S3 URL

WEEK 11 — FRONTEND MVP

74. /login and /register pages — React Hook Form + Zod, JWT storage in memory + refresh cookie

75. Auth Zustand store — user session, role, access token, logout action

76. Axios instance — attach Authorization header, auto-refresh on 401

77. /dashboard — company search bar with debounced TanStack Query + autocomplete

78. Job submission — POST to /api/v1/jobs, navigate to /jobs/[id]

79. JobProgressTracker — SSE EventSource, pipeline step list with status indicators

80. /exports — list with TanStack Query, download button calling /download-url

81. Error boundaries on all pages — graceful fallback UI on network/API failure

WEEKS 12–14 — HARDENING

82. Extraction benchmark: run pipeline for Apple, Microsoft, JPMorgan, Tesla, Walmart

83. Spot-check 135 values (5 companies × 3 statements × 9 fields) against published filings

84. Fix any extraction or mapping errors found in benchmark

85. Celery Beat — currency rates daily, export cleanup daily, source health check 4-hourly

86. Email service — switch to AWS SES for staging, verify domain, test all 5 templates

87. Sentry — integrate SDK in API and all Celery workers

88. Prometheus metrics — export queue depths, job durations, extraction confidence distribution

89. Grafana dashboard — job success rate, p95 response time, worker health

90. GitHub Actions — pr.yml (lint + test), staging.yml (deploy + smoke), release.yml (prod deploy)

91. Production deploy to AWS EC2 — run full Apple/AAPL smoke test end-to-end

92. Confirm job completes in < 3 minutes in production environment

# 4. Folder Structure Blueprint

Create this exact structure before writing any application code. Every folder must exist.

| Path | Purpose |
| --- | --- |
| financial-data-hub/ | Root |
| apps/ | Application layer |
| web/ | Next.js 14 frontend |
| src/app/ | App Router pages |
| (auth)/login/page.tsx | Login page |
| (auth)/register/page.tsx | Register page |
| dashboard/page.tsx | Main dashboard |
| jobs/[id]/page.tsx | Job detail + progress |
| exports/page.tsx | Export history |
| settings/page.tsx | User settings |
| src/components/ | Shared UI components |
| ui/ | shadcn/ui primitives |
| job-tracker/ | SSE progress components |
| financial-grid/ | Data display tables |
| export-builder/ | Export config panel |
| src/hooks/ | Custom React hooks |
| src/lib/ | API client, auth utilities |
| src/stores/ | Zustand stores |
| src/types/ | Auto-generated API types |
| api/ | FastAPI backend |
| main.py | App factory, lifespan |
| core/ | Config, DB, security, exceptions |
| config.py | Pydantic Settings v2 |
| database.py | SQLAlchemy async engine |
| security.py | JWT, bcrypt, token helpers |
| email.py | EmailService abstraction |
| exceptions.py | APIError, error codes |
| email_backends/ | SES, Resend, Console backends |
| email_templates/ | Jinja2 .html + .txt pairs |
| middleware/ | auth.py, audit.py, rate_limit.py |
| models/ | SQLAlchemy ORM model classes |
| routers/ | auth, companies, jobs, financials, exports |
| schemas/ | Pydantic request/response models |
| repositories/ | All database query logic |
| services/ | Domain services (shared by API + workers) |
| acquisition/ | Data discovery and fetching |
| source_registry/ | sources/sec_edgar.py, rate_limiter.py, registry.py |
| company_resolver/ | resolver.py, alias_manager.py |
| document_fetcher/ | fetcher.py, deduplicator.py, storage.py |
| ingestion/ | Document parsing |
| parsers/ | xbrl_parser.py, pdf_parser.py, ocr_parser.py, html_parser.py |
| classifier.py | Document type classification |
| section_detector.py | Find FS pages in PDFs |
| extraction/ | AI and structured extraction |
| schema/ | extraction_schema.py, field_aliases.py |
| prompts/ | income_statement.txt, balance_sheet.txt, cash_flow.txt |
| extractor.py | Claude API orchestration |
| normaliser/ | currency.py, units.py, fiscal_year.py |
| validation/ | Validation engine |
| rules/ | mathematical.py, cross_source.py, trend.py |
| engine.py | Rule orchestrator |
| confidence_scorer.py | Score formula |
| conflict_resolver.py | Multi-source conflict resolution |
| export/ | Excel generation |
| transformer.py | pandas pivot + YoY growth |
| builder.py | openpyxl workbook assembly |
| sheets/ | overview.py, income_statement.py, balance_sheet.py, etc. |
| templates/v1/ | template.xlsx, schema.json |
| workers/ | Celery task definitions |
| celery_app.py | App factory, queue routing config |
| queues.py | Queue name constants |
| tasks/ | acquisition, ingestion, extraction, validation, export, notification tasks |
| db/ | Database management |
| migrations/ | Alembic env.py + versions/ |
| seeds/ | canonical_fields.sql, field_aliases.sql, source_configs.sql |
| alembic.ini | Alembic configuration |
| tests/ | Test suite |
| unit/ | Pure function tests — no database |
| integration/ | Real PostgreSQL + Redis via Docker Compose |
| benchmarks/ | Extraction accuracy tests |
| fixtures/ | 5 sample 10-K filings + expected_values.json |
| infra/ | Infrastructure |
| docker-compose.yml | Local development stack (10 services) |
| Dockerfile.api | FastAPI + Celery worker image |
| Dockerfile.web | Next.js image (prod only) |
| nginx/ | nginx.conf for local reverse proxy |
| .github/ | GitHub configuration |
| workflows/ | pr.yml, staging.yml, release.yml |
| PULL_REQUEST_TEMPLATE.md | PR checklist |
| .env.example | All env vars listed, no values |
| pyproject.toml | Python dependencies (uv/Poetry) |
| README.md | Setup instructions |

# 5. Technology Initialisation Sequence

Run in this order. Each step depends on the previous.

| # | Action | Command / Action Detail | Purpose |
| --- | --- | --- | --- |
| 1 | Install uv | pip install uv (or brew install uv on Mac) | Python package manager |
| 2 | Initialise Python project | uv init (run in repo root) | Creates pyproject.toml |
| 3 | Create virtual environment | uv venv | Creates .venv/ |
| 4 | Install Python deps | uv sync | Installs from pyproject.toml |
| 5 | Initialise Alembic | cd db && alembic init migrations | Creates alembic.ini + env.py |
| 6 | Configure Alembic env.py | Set target_metadata = Base.metadata, read DATABASE_URL from env | Connects Alembic to SQLAlchemy models |
| 7 | Create Next.js app | cd apps/web && npx create-next-app@latest . --typescript --tailwind --app --src-dir --no-git | Scaffolds frontend |
| 8 | Install frontend deps | cd apps/web && npm install (packages listed in Section 6) | Installs all frontend packages |
| 9 | Configure TypeScript | Set strict: true, paths: {"@/*": ["./src/*"]} in tsconfig.json | Enables strict mode + aliases |
| 10 | Start Docker stack | docker compose up --build -d | Starts all 10 local services |
| 11 | Verify DB connection | docker compose exec api python -c "from core.database import engine; print(engine)" | Confirms DB reachable |
| 12 | Run first migration | cd db && alembic upgrade head | Creates all tables in local PostgreSQL |
| 13 | Run seeds | psql $DATABASE_URL -f seeds/canonical_fields.sql && -f seeds/field_aliases.sql && -f seeds/source_configs.sql | Populates reference data |
| 14 | Verify seeds | psql $DATABASE_URL -c "SELECT COUNT(*) FROM canonical_fields;" -- expect 52 | Confirms 52 canonical fields across 3 statements |
| 15 | Generate TS types | cd apps/web && npx openapi-typescript http://localhost:8000/api/v1/openapi.json -o src/types/api.ts | Generates typed API client — run after every API change |

# 6. Dependencies to Install

Python Dependencies (pyproject.toml)

| Package | Version | Purpose |
| --- | --- | --- |
| fastapi | 0.115+ | Web framework |
| uvicorn[standard] | latest | ASGI server |
| sqlalchemy[asyncio] | 2.x | ORM with async support |
| alembic | latest | Database migrations |
| asyncpg | latest | Async PostgreSQL driver |
| psycopg2-binary | latest | Sync PostgreSQL driver (Alembic) |
| pydantic | 2.x | Data validation and settings |
| pydantic-settings | 2.x | Environment variable loading |
| python-jose[cryptography] | latest | JWT encode / decode |
| passlib[bcrypt] | latest | Password hashing |
| python-multipart | latest | Form data in FastAPI |
| celery[redis] | 5.x | Task queue |
| redis | 5.x | Redis client |
| boto3 | latest | AWS S3 + SES + Secrets Manager |
| pandas | 2.x | Data transformation for Excel export |
| openpyxl | 3.x | Excel workbook generation |
| pdfplumber | latest | Native PDF table extraction |
| camelot-py[cv] | latest | PDF table extraction (bordered tables) |
| pymupdf | latest | PDF text extraction |
| arelle-release | latest | XBRL / iXBRL parser (SEC filings) |
| jinja2 | 3.x | Email template rendering |
| resend | latest | Resend email SDK (dev/staging) |
| structlog | latest | Structured JSON logging |
| opentelemetry-sdk | latest | Distributed tracing |
| opentelemetry-instrumentation-fastapi | latest | Auto-instrument FastAPI |
| sentry-sdk[fastapi] | latest | Error tracking |
| httpx | latest | Async HTTP client (EDGAR API calls) |
| pyotp | latest | TOTP for MFA |
| python-slugify | latest | Slug generation for company names |
| pytest | latest | Test framework (dev dependency) |
| pytest-asyncio | latest | Async test support (dev dependency) |
| pytest-cov | latest | Coverage reporting (dev dependency) |
| ruff | latest | Python linter and formatter (dev dependency) |
| mypy | latest | Static type checker (dev dependency) |

Frontend Dependencies (npm install)

| Package | Version | Purpose |
| --- | --- | --- |
| next | 14+ | Framework |
| react / react-dom | 18+ | UI library |
| typescript | 5.x | Language |
| tailwindcss | 3.x | Styling |
| @tanstack/react-query | 5.x | Server state management |
| @tanstack/react-table | 8.x | Headless data tables |
| zustand | 4.x | Client state management |
| react-hook-form | latest | Form management |
| zod | latest | Schema validation |
| axios | latest | HTTP client |
| @radix-ui/react-* | latest | Accessible UI primitives |
| class-variance-authority | latest | shadcn/ui variant helper |
| clsx | latest | Conditional class names |
| tailwind-merge | latest | Merge Tailwind classes safely |
| lucide-react | latest | Icon library |
| openapi-typescript | latest | Generate TS types from OpenAPI spec (dev dep) |
| eslint / @typescript-eslint/* | latest | Linting (dev dep) |

# 7. Estimated Implementation Effort

Based on a team of 2 engineers: 1 backend (Python), 1 frontend (Next.js/TypeScript).

Backend engineer also handles DevOps, database, and Celery configuration.

| Milestone | Calendar Time | Engineer Allocation | Notes |
| --- | --- | --- | --- |
| Pre-Development (M0) | 1 week | 0.5 BE + 0.5 FE | Repo, Docker, schema, seeds, AWS, EDGAR proof-of-concept |
| Foundation Layer (M1) | 2 weeks | 1.5 BE + 0.5 FE | FastAPI, auth, middleware, database — most foundational work |
| Company Resolution (M2) | 1 week | 1.0 BE + 0.0 FE | EDGAR API, fuzzy matching, job pipeline skeleton |
| Document Acquisition (M3) | 2 weeks | 1.0 BE + 0.0 FE | EDGAR fetch, S3, deduplication, rate limiting |
| XBRL Extraction (M4) | 2 weeks | 1.5 BE + 0.0 FE | XBRL parser is the highest-complexity work in Phase 1 |
| Validation Engine (M5) | 1 week | 1.0 BE + 0.0 FE | 13 rules, confidence scorer — well-defined, fast to implement |
| Excel Export (M6) | 2 weeks | 1.0 BE + 0.5 FE | pandas transform + openpyxl — significant formatting work |
| Frontend MVP (M7) | 1 week | 0.5 BE + 1.5 FE | Login, dashboard, search, SSE, download — mostly frontend |
| Hardening + Launch (M8) | 3 weeks | 1.0 BE + 0.5 FE | Benchmarks, email, monitoring, CI/CD, production deploy |
| TOTAL | 15 weeks (some parallel) | ~14 BE-weeks + ~4 FE-weeks | 18 total engineer-weeks |

Effort Risk Factors

| Risk Level | Description |
| --- | --- |
| HIGH risk | XBRL parser integration — arelle has a steep learning curve; allow extra 3 days buffer on M4 |
| HIGH risk | Excel formatting to spec — number formats, conditional formatting, and freeze panes take longer than expected |
| MEDIUM risk | EDGAR rate limiting — if IP is throttled, document fetch for M3 may take 2x longer |
| MEDIUM risk | iXBRL concept mapping — field_aliases seed data may need additions after first test on real filings |
| LOW risk | Auth and database work — well-understood patterns, low variability |
| LOW risk | Frontend MVP — shadcn/ui components accelerate UI development significantly |

Velocity Assumptions

• 2 engineers working full-time (40h/week each)

• No significant scope changes after implementation begins

• EDGAR API remains stable and accessible throughout development

• Claude API quota sufficient for Phase 2 AI extraction (not needed for Phase 1 XBRL path)

• AWS infrastructure provisioned and accessible within Week 0

• Extraction benchmark fixtures (5 company 10-K filings) prepared before M8

# Ready to Build

All planning, architecture, and specification work is complete. This guide contains everything needed to begin implementation in a fresh session. Hand this document to the implementation session along with the three-part Engineering Specification Report.

Documents to reference during implementation:

| Document | Reference For |
| --- | --- |
| Engineering_Specification_Part_1.docx | Database schema, backend architecture, frontend stack, ingestion pipeline |
| Engineering_Specification_Part_2.docx | Canonical field schemas, validation rules, Excel workbook spec, auth design, Celery queues |
| Engineering_Specification_Part_3.docx | File storage, API endpoints, logging/monitoring, deployment, email service, Appendix A checklist, Appendix B tech decisions |
| Phase_1_Implementation_Guide.docx | This document — step-by-step execution order |
| PROJECT REQUIREMENTS.docx | Product requirements and success criteria |
| Development Phases.docx | Revised phase structure (Validation in Phase 1) |

Start with Step 1 of Section 3. Do not skip steps. Do not proceed past a milestone gate until it passes.